## Action Log
Action ID | Date Opened | Date Due | Action | Owner | Status | Action Update
1022/01 | 2022-10-18 |  | CMAG Secretariat to update the ToR to include expectation for Delivery Partners to attend all CMAG meetings. | Elexon | Closed | The CMAG Terms of Reference were updated, approved and are available to view on the website.
1022/02 | 2022-10-18 |  | CMAG Secretariat to include ‘CMAG Representative Updates’ as a standing agenda item for future meetings. | Elexon | Closed | This has been included as a standing agenda item for CMAG.
1022/03 | 2022-10-18 |  | Members to provide contact information on their Alternate to the CMAG Secretariat. | CMAG Members | Closed | All Alternates have been confirmed, those that are not currently CMAG Members are to be ratified by Ofgem.
1022/04 | 2022-10-18 |  | CMAG Secretariat to publish the Change Log on the CMAG website. | Elexon | Closed | The CMAG Change Log is available to view on the website.
1022/05 | 2022-10-18 |  | CMAG Secretariat to review how other codes prioritise changes and consider alternative options for the CMAG Prioritisation Tool. | Elexon | Closed | An update was provided at CMAG Meeting 2 and the group agreed to progress with the CMAG prioritisation tool.
1022/06 | 2022-10-18 |  | CMAG Members to review the backlog of Change Proposals and provide each with a priority level of High, Medium or Low using the proposed CMAG prioritisation tool, by 1 November 2022. | CMAG Members | Closed | CMAG Members provided their prioritisation views and an update was provided at CMAG Meeting 2.
1022/07 | 2022-10-18 |  | Ofgem to review the Triton Power Change Proposal displayed on the Ofgem website. | Ofgem | Closed | Triton Power has confirmed it is not seeking to raise a formal Change Proposal based on its consultation response.
1122/01 | 2022-11-15 |  | Ofgem and National Grid Delivery Body to provide clarity on whether mid-year CM Rules changes are allowed, and any constraints that may be in place. | Ofgem | Closed | Ofgem is awaiting feedback from its legal team. From an EMR DB deliverability perspective, whether a mid-year CM Rules change can be implemented by the DB will depend on the scale and nature of the change.
1122/02 | 2022-11-15 |  | National Grid Delivery Body to confirm how it would respond to, and the impacts on the CM of, a to partial or total market suspension. | EMR DB | Closed | Pursuant to Rule 8.5.1, Capacity Providers are obliged to deliver the ALFCO of their capacity committed CMU in the event of a Capacity Market Notice. They have no obligation, however, in any Settlement Period during which the Capacity Committed CMU is affected by a suspension under section G (Contingencies) of the BSC.
1122/03 | 2022-11-15 |  | The NGESO Representative to share details with CMAG on the NGESO User Group for Portal update testing. | EMR DB | Closed | Please email Firas Sultan on box.NewEMR.ITteam@nationalgrid.com to register your interest in the EMR Portal User Group.
1122/04 | 2022-11-15 |  | CMAG Members to provide their initial views on urgent Change Proposal CP367 and whether it should be considered further by CMAG. | CMAG Members | Closed | CMAG Members views are that CP367 should not be considered further by CMAG.
1122/05 | 2022-11-15 |  | The Ofgem Representative to provide further information on the process and timescales for laying CM Rules Changes in parliament. | Ofgem | Closed | A BEIS FAQ document on laying rules before Parliament has been circulated with the Meeting 3 paper pack.
1122/06 | 2022-11-15 |  | CMAG Members to review the CMAG Operating Procedure and provide any comments to the Secretariat by 25 November 2022. | CMAG Members | Closed | The CMAG Operating Procedure has been circulated with the Meeting 3 paper pack.
1122/07 | 2022-11-15 |  | The Ofgem Representative to provide an updated view on whether CP364 should be considered Urgent. | Ofgem | Closed | Ofgem's view is that CP364 should not be considered urgent.
1122/08 | 2022-11-15 |  | CMAG Members to consider whether any additional specific questions are required for CP364 and feedback to the CMAG Secretariat for consideration at the next meeting. | CMAG Members | Closed | An update was provided at CMAG Meeting 3.
1122/09 | 2022-11-15 |  | CMAG Members to consider whether any additional specific questions are required for CP365 & 366, and feedback to the CMAG Secretariat for consideration at the next meeting. | CMAG Members | Closed | An update was provided at CMAG Meeting 3.
1222/01 | 2022-12-13 |  | ESNZ and Ofgem to confirm the policy intention and history of Secondary Trading being limited till after T-1 auctions (and if possible, further history on deadlines around Secondary Trading). | DESNZ | Closed | The Ofgem representative noted the purpose of restricting secondary trading until after the year ahead auction and the limited time window for physical trading was to prevent parties that fail to build new plants on time from profiting from higher prices in the year head auction.
1222/02 | 2022-12-13 |  | NGESO, LCCC and EDF to confirm the proposed concept and impacts of weighted PTCO noted in CP364. | EMR DB | Closed | CMAG agreed to hold a workgroup to discuss the proposed concept and impacts of weighted PTCO in CP364.
1222/03 | 2022-12-13 |  | NGESO and Elexon to confirm its view on the impacts of CP364 on CM Credit Cover and prequalification. | EMR DB | Closed | Elexon has confirmed that moving the trading window to 6 weeks before the T-1 will have no impact on the Credit Cover process. It was also confirmed in the CMAG meeting that there would be no impact on prequalification.
1222/04 | 2022-12-13 |  | Elexon to provide clarity on whether DSRs turning on/off should be factored into the calculation for CP364. | Elexon | Closed | To be discussed as part of the CP364 workgroup.
1222/05 | 2022-12-13 |  | Ofgem to confirm the history of any previous concern on unintended consequences of CP364, specifically speculative bidding as a result of secondary trading. | Ofgem | Closed | To be discussed as part of the CP364 workgroup.
1222/06 | 2022-12-13 |  | NGESO to complete an impact assessment for CP364. | EMR DB | Closed | To be discussed as part of the CP364 workgroup.
1222/07 | 2022-12-13 |  | Elexon to deliver the draft legal text for CP364 for CMAG Members to review. | Elexon | Closed | The draft legal text for CP364 is available in the CMAG Meeting 4 slide pack.
1222/08 | 2022-12-13 |  | LCCC to include additional clarity on CM suspension in the updated stress event guidance to be drafted. | LCCC to | Closed | LCCC have included a section on Black Starts in the latest Stress Event Guidance document (v4.0) that was published on 21st December. Available at: https://www.emrsettlement.co.uk/document/guidance/g18-capacity-market-stress-event-guide.
1222/09 | 2022-12-13 |  | Elexon to update the CMAG website with the information provided by Ofgem regarding its legal limits to enact CM Rules changes. | Elexon | Closed | This information is available on the change proposals page of the CMAG website.
1222/10 | 2022-12-13 |  | Ofgem to confirm if the restricted component parts of CM Agreements that are grandfathered also applies to secondary trades. | Ofgem | Closed | Ofgem has confirmed the restricted component parts of CM Agreements that are grandfathered do apply to secondary trades.
1222/11 | 2022-12-13 |  | NGESO to confirm the total number of ITE reports received in the last 5 years and what they are used for. | EMR DB | Closed | The NGESO representative noted ITE reports are not used by NGESO.
1222/12 | 2022-12-13 |  | NGESO to complete an impact assessment for CP365. | EMR DB | Closed | A full impact assessment can be found in the CP365 CM Rules Change Report.
1222/13 | 2022-12-13 |  | Elexon to deliver the draft legal text for CP365 for CMAG Members to review. | Elexon | Closed | The draft legal text for CP365 is available in the CMAG Meeting 4 slide pack.
1222/14 | 2022-12-13 |  | NGESO to complete an impact assessment for CP366. | EMR DB | Closed | A full impact assessment can be found in the CP366 CM Rules Change Report.
1222/15 | 2022-12-13 |  | Elexon to deliver the draft legal text for CP366 for CMAG Members to review. | Elexon | Closed | The draft legal text for CP366 is available in the CMAG Meeting 4 slide pack.
1222/16 | 2022-12-13 |  | Members to provide their prioritisation scores for CP368 and CP369 by Friday 16 December 2022. | EMR DB | Closed | Update to be provided at the meeting.
1222/17 | 2022-12-13 |  | CMAG Secretariat to circulate a survey for feedback on CMAG meetings to all CMAG Members. | Elexon | Closed | The CMAG Feedback Survey was circulated to all Members and Representatives on Friday 6th January 2023.
1222/18 | 2022-12-13 |  | CMAG Members to respond to the survey and provide feedback to the CMAG Secretariat. | CMAG Members | Closed | An updated on the feedback received will be provided at CMAG Meeting 5.
0123/01 | 2023-01-17 |  | Elexon to draft a secondary trading approach, including CP364, CP356, CP362 and CP369, to be presented at the next CMAG Meeting. | Elexon | Closed | Secondary Trading approach initially presented and discussed at CMAG meeting 5. At CMAG Meeting 6, it was agreed to review Agreements and Obligations Risks.
0123/02 | 2022-01-17 |  | CMAG Members to confirm to the Secretariat any issue areas with secondary trading within the CM Rules to be addressed at the next CMAG Meeting. | CMAG Members | Closed | Update to be provided at the meeting.
0123/03 | 2022-01-17 |  | The LCCC/ESC representative to share information from the LCCC/ESC review of secondary trading arrangements with CMAG. | LCCC | Closed | LCCC/ESC is reviewing its previous proposal on secondary trading and will present this at the CP364 workgroup.
0123/04 | 2022-01-17 |  | Elexon to arrange a workgroup to discuss and develop the details and solution for CP364 further, inviting wider industry participants where appropriate. | Elexon | Closed | The CP364 Sub-group will be held on Monday 6 March 2023 from 10:00 till 16:00 via Microsoft Teams. Please contact CMAG@elexon.co.uk if you are interested in joining.
0123/05 | 2023-01-17 |  | The DESNZ representative to provide an update on the new Subsidy Control Framework and the parameters under which a CP would need to be considered by this group. | DESNZ | Closed | This action is being considered as part of the CMAG Process Review.
0123/06 | 2023-01-17 |  | The EMR Delivery Body representative to confirm their interpretation of Rule 9.2.5(a)(i) and the intention behind it. | EMR DB | Closed | The EMR DB documents the interpretation of CM Rules in its guidance published on its website. This interpretation can originate from within EMR DB but can also be from Ofgem or DESNZ where EMR DB has sought clarification of the original policy intent. The EMR DB interpretation of Rule 9.2.5(a)(i) has been confirmed by DESNZ at CMAG Meeting 5.
0123/07 | 2022-01-17 |  | The Ofgem representative to complete an initial review of CP360 and provide its minded to position at CMAG Meeting 5. | EMR DB | Closed | Ofgem has noted its minded-to position to reject CP360 without further development due to its overlap with current government policy direction on net zero.
0123/08 | 2023-01-17 |  | CMAG Members to review CP360 and provide their initial view at CMAG Meeting 5, on whether CP360 should be taken forward. | CMAG Members | Closed | Ofgem presented their view that CP360 should not be progressed on the basis that DESNZ would be better placed than the CMAG to progress a change of this magnitude. CMAG Members agreed with this rationale.
0123/09 | 2023-01-17 |  | NGESO to hold meeting with CP363 Proposer to discuss proposal and changes made to EMR portal. | EMR DB | Closed | Propose to close this action, following an update on Action 0323/06 regarding MFA authentication for the Portal at CMAG Meeting 6.
0223/01 | 2023-03-02 |  | Ofgem to consider confidential change process and process of submitting confidential evidence to Ofgem, along with the criteria for urgency of CM Rules Change Proposals. | Ofgem | Closed | An update was presented at CMAG Meeting 7 and will be circulated with the draft minutes from the meeting.
0223/02 | 2023-03-02 |  | The EMR Delivery Body to provide information on the number of secondary trading requests that are processed and rejected, and the CMU relocation process requests. | EMR DB | Closed | An update was presented at CMAG Meeting 6 and can be found in the slide pack.
0223/03 | 2023-03-02 |  | DESNZ to provide guidance on the policy intent for Secondary Trading so that the CMAG can proceed with its Secondary Trading work in alignment to DESNZ views | DESNZ | Closed | This action is being considered as part of the CMAG Process Review.
0223/04 | 2023-03-02 |  | CMAG Members to provide any further thoughts on how to consider secondary trading so that a formal plan can be generated. | CMAG Members | Closed | CMAG Members have agreed to review SPDs and Agreements/Obligations risk in relation to Secondary Trading.
0223/05 | 2023-03-02 |  | LCCC and NGESO-DB to work offline on alternative options relating to the 'Capacity Market Secondary Trading Development' slides to be presented in April to CMAG. | LCCC | Closed | An update was presented at CMAG Meeting 7 and can be found in the slide pack.
0223/06 | 2023-03-02 |  | The EMR Delivery Body to consider the need for multi-factor authentication on its portal and present back to CMAG | EMR DB | Closed | Although the CM Rules define Applicant Confidential Information, the Rules do not cover security arrangements to manage access to this information. This issue is therefore considered to be outside the scope of CMAG’s remit. The appropriateness of security issues should be addressed through the project for the new EMR DB Portal, in which industry representatives have been actively participating.
0223/07 | 2023-03-02 |  | DESNZ to provide further information to the CMAG in relation to further development of the CP362 and whether the proposal is impacted by the subsidy control framework | DESNZ | Closed | DESNZ has confirmed that the alternative solution to CP362, presented at CMAG Meeting 6, is not impacted by the subsidy control framework and CMAG can continue further development of this proposal.
0223/08 | 2023-03-02 |  | LW and RaT to develop revised CP362 drafting and share with CMAG Secretariat | LW and RaT | Closed | Updated legal text presented at CMAG Meeting 6 was approved by CMAG Members.
0223/09 | 2023-03-02 |  | CMAG Members to advertise the CMAG Distribution List to CM contacts | CMAG Members | Closed | CMAG Members are requested to continue to inform interested stakeholders of the CMAG Distribution List and monthly newsletter.
0323/01 | 2023-03-21 |  | The Ofgem representative to provide an update on the expected timelines for consultation and decision for CP365, CP366 and CP368. | Ofgem | Closed | An update was presented at CMAG Meeting 7 and will be circulated with the draft minutes from the meeting.
0323/02 | 2023-03-21 | 2023-06-13 | The DESNZ representative to provide information regarding the DESNZ spring Consultation on the Industry Supercharger to the CMAG Secretariat for circulation. | DESNZ | Closed | to be shared by end of week.
0323/03 | 2023-03-21 |  | The LCCC/ESC representative to provide an update on lessons learned from the mock stress event in 2018, to be presented to CMAG. | LCCC | Closed | An update was presented at CMAG Meeting 7 and can be found in the slide pack.
0323/04 | 2023-03-21 |  | The Ofgem representative to confirm the history behind Rule 4.4.4, and outputs from its 5 year review of the CM. | Ofgem | Closed | An update was presented at CMAG Meeting 7 and will be circulated with the draft minutes from the meeting.
0323/05 | 2023-03-21 |  | The DESNZ representative to confirm what constitutes a change of configuration in Rule 4.4.4 and the policy intent behind this Rule. | DESNZ | Closed | This action is under consideration as part of DESNZ’s plans for communicating policy intent via formal publication (e.g. consultations etc).
0423/01 | 2023-04-18 | 2023-06-13 | The DESNZ representative to look at the current timeline for Auctions and assess any possible changes to bring forward the auction timeline to allow for four full years for delivery. | DESNZ | Closed | DESNZ continues to keep this under review.
0423/02 | 2023-04-18 | 2023-05-09 | Elexon to review Rule 4.4.4 alongside the proposed changes within the Ofgem 5 year review of the CM and present a proposed route forwards for CMAG to discuss. | Elexon | Closed | Update presented at CMAG Meeting 8.
0423/03 | 2023-04-18 | 2023-05-09 | The EMR DB representative to confirm its assurance process for a CMU that has notified the EMR DB it was participating in a Relevant Balancing Service during a System Stress Event. | EMR DB | Closed | Following an SSE (System Stress Event), EMR DB collects and compiles Relevant Balancing Services (RBS) and Relevant Interruption (RI) data from Capacity Providers using SSE template. The RBS and RI data is validated with the ESO’s Contracts/Settlements team.
0423/04 | 2023-04-18 | 2023-05-09 | Elexon to consider a draft Change Proposal on the process for disputing penalties as a result of a System Stress Event. | Elexon | Closed | Update presented at CMAG Meeting 8.
0423/05 | 2023-04-18 | 2023-06-13 | The EMR DB representative to provide further clarity on its interpretation of Rule 13.4 in relation to the timings provided in its guidance on traded obligations and SPDs. | EMR DB | Closed | We assume the action relates to Step 9 Option 2 in our Secondary Trading guidance which says “CMU has completed the SPDs and you believe those will meet the requirements as per CM Rule 9.2.6(ii)(bb)”. The intention of this part of the guidance is to identify that SPDs which have been passed could be used as evidence that the Transferee has delivered a capacity at least equal to its de-rated capacity in any settlement period falling within six months prior to the first date within the relevant delivery year, as required under the Rules. It is not intended to say that SPDs must be completed at that point in time before a trade can be made. We agree the guidance could be clearer on this point and are pleased to be able to clarify the intention.
0423/06 | 2023-04-18 | 2023-06-13 | The EMR DB representative to confirm where the obligation lies in the Rules for CMUs to be required to complete an SPD before trading, as noted in its guidance. | EMR DB | Closed | Update as per Action 0423/05.
0423/07 | 2023-04-18 | 2023-05-09 | Elexon to work with EMR DB, Raoul Thulin and Lisa Waters to update the draft legal text for CP362 following feedback at CMAG Meeting 7. | Elexon | Closed | Update presented at CMAG Meeting 9.
0423/08 | 2023-04-18 | 2023-05-09 | The EMR DB representative to confirm if an impact assessment is required from the EMR DB for CP369. | EMR DB | Closed | EMR DB believes that CP369 may result in impacts on EMR DB processes. EMR DB will undertake an impact assessment for CP369.
0423/09 | 2023-04-18 | 2023-05-09 | Elexon and LCCC/ESC to update the draft legal text for CP369 following feedback at CMAG meeting 7. | Elexon and LCCC/ESC | Closed | Update presented at CMAG Meeting 8.
0423/10 | 2023-04-18 | 2023-05-09 | LCCC/ESC and Elexon representative to draft a timeline of the current process for submitting aggregation rules through to completing a trade. | LCCC/ESC and Elexon | Closed | Update presented at CMAG Meeting 8.
0423/11 | 2023-04-18 | 2023-05-09 | Elexon to update its Forward Workplan to include the additional workstreams and issue areas under discussion by CMAG. | Elexon | Closed | The updated Forward Workplan will be presented at CMAG Meeting 8 and made available publicly via the CMAG website.
0423/12 | 2023-04-18 | 2023-05-09 | The EMR DB representative to review its termination notice communications and confirm how a Capacity Participant can identify the terminated CMU within the notice. | EMR DB | Closed | Termination notifications generated automatically from the EMR Portal do not include details of CMUs. This change was instigated following an incident in which some automated Portal emails containing confidential CMU information were sent to incorrect email addresses. To avoid this happening again, the CEMRAI information was removed from automated termination emails. To address the reduced information in these Portal notifications, they are always followed up with an email sent from the EMR DB Agreements team manager to the Company’s Main Admin, and sometimes the Deputy Main Admin. These emails always identify the relevant CMUs and associated CAN (Capacity Agreement Notice). Attached to each email is a standard template letter which also identifies the CMU specific information. EMR DB aims to send these emails on the same day as the automated Portal emails. The of issue dates of both are recorded to track variations.
0523/01 | 2023-05-16 | 2023-06-13 | Members to review live CM Rules Change Proposals to assess if they consider any should be a priority for the new EMR Portal, at CMAG Meeting 9. | CMAG Members | Closed | In agreement with EMR DB, this action will be revisited once additional new CM Rules Change Proposals have been submitted by EMR DB.
0523/02 | 2023-05-16 | 2023-06-13 | The EMR DB representative to confirm the touchpoints during the year where the EMR Portal is not available and the impact of this on Participants. | EMR DB | Closed | Within the Legacy System, all relevant Milestones have the relevant Working Day deadline for input for each individual Capacity Auction, with a Working Day defined by the Regulations as closing at 5pm on that specific day. This means that the Portal’s functionality of being able to upload is disabled once the Working day has passed the deadline. Where there is specific evidence, due to system issues or DESNZ offering an extension, we are able to allow the Capacity Provider to be able to upload within Other Documents in order to meet a relevant deadline. This does mean that the relevant documentation is not stored in the correct area within the Legacy system due to the relevant functionality still being disabled. In Portal V2, the Post Assessment Request (PAR) for the relevant milestone can be re-opened post deadline by the Delivery Body to allow the Capacity Provider to upload the correct documentation into the correct area. V2 will also enable a Secure Share functionality to share relevant evidence documentation which does not facilitate a specific milestone.
0523/03 | 2023-05-16 | 2023-06-13 | The LCCC/ESC representative to advise the CMAG how it plans to seek industry feedback on its Delivery Body/Settlement Body process exploration work. | LCCC/ESC | Closed | Update to be provided at CMAG Meeting 10. The slides have been circulated to CMAG for review, with feedback requested by Friday 7 July 2023.
0523/04 | 2023-05-16 | 2023-06-13 | The LCCC/ESC representative to confirm with the EMR DB the required lead time for submitting aggregation rules prior to secondary trading both in year and outside of the delivery year. | LCCC/ESC | Closed | The LCCC/ESC representative has confirmed the lead time for submitting aggregation rules is 5WD, and the legal text for CP369 will be updated in line with this.
0523/06 | 2023-05-16 | 2023-06-13 | The LCCC/ESC representative to review the penalty calculations in the Regulations and confirm where it is noted that penalty calculations are not reconciled. | LCCC/ESC | Closed | Update presented at CMAG Meeting 9.
0523/07 | 2023-05-16 | 2023-06-13 | CMAG Secretariat to confirm what the process is where the disputes body determines the disputing party is correct in a dispute. | Elexon | Closed | Update presented at CMAG Meeting 9.
0623/01 | 2023-06-20 | 2023-07-11 | The LCCC/ESC representative to share information regarding MHHS impact on the D0357 and D0355 flows, to be circulated to CMAG. | LCCC/ESC | Closed | LCCC/ESC has shared this with the CMAG Secretariat, and it was circulated to CMAG with the Draft Minutes from CMAG Meeting 9.
0623/02 | 2023-06-20 | 2023-07-11 | The Ofgem representative to provide a diagram on Ofgem's process for a CM Rules Change Proposal following receipt of a CMAG recommendation. | Ofgem | Closed | Update provided on bi-annual change process at CMAG Meeting 10.
0623/03 | 2023-06-20 | 2023-07-11 | The Ofgem representative to confirm Ofgem's process and timelines for dealing with urgent CM Rules Change Proposals. | Ofgem | Closed | Update provided on bi-annual change process at CMAG Meeting 10.
0623/04 | 2023-06-20 | 2023-08-08 | CMAG Members to review the CP362 legal text and confirm their recommendation to approve or reject CP362 ex-committee. | CMAG Members | In Progress | The CMAG Secretariat has circulated the CP362 legal text options to CMAG Members for review and vote. An update will be presented at CMAG Meeting 11.
0623/05 | 2023-06-20 | 2023-08-08 | CMAG Members to review the CP369 legal text and confirm their recommendation to approve or reject CP369 ex-committee. | CMAG Members | In Progress | The CMAG Secretariat will circulate the CP369 legal text to CMAG Members for review and vote.
0623/06 | 2023-06-20 | 2023-07-11 | The CMAG Secretariat to draft a CM Rules Change Proposal for Rule 4.4.4, to be discussed at CMAG Meeting 10. | Elexon | Closed | The CMAG Secretariat has drafted CP372 'Change to Rule 4.4.4', circulated with the CMAG Meeting 10 materials.
0723/01 | 2023-07-18 | 2023-08-08 | The CMAG Secretariat to draft further options to mitigate the connections delay issue raised in CP371, given that the original proposal may be contrary to policy intent. | Elexon | In Progress | Update to be provided at the meeting.
0723/02 | 2023-07-18 | 2023-09-14 | The Ofgem representative to clarify the policy intent behind Rule 2.3.3 and the De-rating Factors that secondary trading entrants and acceptable transferees use. | Ofgem | In Progress | Update to be provided at CMAG Meeting 12.
0723/03 | 2023-07-18 | 2023-09-14 | The CMAG Secretariat to review whether a change to Rule 2.3.3 is needed, and draft a change proposal for CMAG where it is required. | Elexon | Complete | Raoul Thulin has drafted a change proposal to Rule 2.3.3, to be discussed at CMAG Meeting 12.
0723/04 | 2023-07-18 | 2023-08-08 | The CMAG Secretariat to review the solution for CP372 to include effective controls and verification to preserve the integrity of Prequalification. | Elexon | In Progress | Update to be provided at the meeting.
0723/05 | 2023-07-18 | 2023-08-08 | The EMR DB representative to confirm what impact the Portal V2 will have on the administrative cost and process of component reallocation, and whether this will be made more cost effective/simpler. | EMR DB | In Progress | Update to be provided at the meeting.

## CMAG Requests
Requests Log
Meeting Requested | Request | Owner | Status | Update
Meeting 4 | The DESNZ representative to provide an update on the new Subsidy Control Framework and the parameters under which a CP would need to be considered by this group.
Meeting 5 | There is no appeals system for the Capacity Market when there are differing interpretations of CM Rules between Participants and the Settlement Body or Delivery Body. There should be a process which allows for an appeal to Ofgem or DESNZ.
Meeting 5 | Create a repository where all information from the CM for all parties could be gathered to make it easier for viewers.
Meeting 7 | The DESNZ representative to look at the current timeline for Auctions and assess any possible changes to bring forward the auction timeline to allow for four full years for delivery.
Meeting 7 | Participants cannot see what their submitted data during a mock stress event looks like on the receiving end so are unable to make changes where required until they receive a corresponding report from the SB. Further clarity around this would be useful.
Meeting 7 | Publish the Aggregation Rule formula in a defined location so that CPs know where it is and what it is.
Meeting 7 | Create separate guidance on EPT for new battery CPs who are due to enter prequalification so there is harmony between battery developers.
Meeting 8 | Termination notices issued by the EMR DB should be issued to both the Company's Main Admin and Deputy Main Admin in all cases. | EMR DB | Actioned | The EMR DB representative notified CMAG at Meeting 9 that EMR DB will now issue Termination Notices to both the Company's Main Admin and Deputy Main Admin moving forwards.