CM Rules Change Proposal – CP365 ITE Report Requirements

CP365 seeks to remove the requirement for an assessment from an ITE where a construction milestone has moved more than two months earlier from that set out in the Construction Plan in the pre-qualification application.

CP365 will impact Capacity Market Participants.

Table of Contents

Table of Contents	1

Executive Summary	2

Issue	3

Solution	3

Prioritisation	3

CMAG Development/Discussions	3

Impacts & Costs	4

Views against CM Rules Change Objectives and Ofgem’s Principal Objective	4

Delivery Partners Comments	5

Implementation Date	5

Recommendations	5

Appendix 1 – Key Questions for CP365	5

## Executive Summary

- Issue

- Rule 12.2.1 requires a Capacity Provider to submit progress reports to the EMR Delivery Body every 6 months setting out when construction milestones are expected to be achieved. If the earliest and latest dates for these construction milestones move beyond two months, it is considered a material change and an assessment is required by an Independent Technical Expert (ITE). If the forecasted earliest and latest dates are close together, any changes to the project timeline are likely to cause a material change.

- Solution

This Change Proposal seeks to remove the requirement for an assessment from an ITE where a construction milestone has moved more than two months earlier from that set out in the Construction Plan in the pre-qualification application.

Impacts and Costs

TBC following NGESO Impact Assessment response.

| - Costs Estimates |  |  |  |
| --- | --- | --- | --- |
| - Organisation | - Impacts | - Implementation (£k) | - On-going (£k/annum) |
| - LCCC/ESC | - No impacts on systems and processes have been identified. | - None | - None |
| - Delivery Body/NGESO | - TBC | - TBC | - TBC |
| - Industry | - Positive impact. | - None | - None |
| - Total | - TBC | - TBC | - TBC |

Implementation

TBD by CMAG at CMAG Meeting 4 on 17 January 2023.

Recommendation

The CMAG initially recommends to the Authority:

- That CP365 should be approved;

- That CP365:

  - Better facilitates Ofgem’s Principal Objective

  - Better facilitates promoting investment in capacity to ensure security of electricity supply

  - Better facilitates the efficient operation and administration of the Capacity Market

- An Implementation Date for CP365 of July 2023 or as soon as practicable afterwards if this date is not achievable

- That the legal text for CP365 be approved.

## Issue

- Rule 12.2.1 requires new build and refurbishing Capacity Market Units (CMUs) to submit progress reports from after the Auction to the start of the Delivery Year (8 reports in total). If milestone dates in these reports have moved forward or backward by more than 2 months compared to the last submitted report, Rule 12.2.1(c) requires an assessment report from an Independent Technical Expert. If the forecast earliest and latest dates are too close together then any changes to the project timeline are likely to cause a material change.

- Each ITE report can costs thousands of pound per CMU, with an estimated total cost of £1.6 million spent on ITE reports in a delivery year.

- There is no consequence for failure to submit an ITE report or submitting one that does not meet the criteria set out in the Rules.

## Solution

CP365 seeks to address this by removing the requirement for an assessment from an Independent Technical Expert if construction milestones have moved by more than 2 months from that set out in the Construction Plan in the pre-qualification application.

- It is proposed that Rule 12.2.1 (c) be deleted, requiring an explanation for a material change only where milestone dates are two or more months later than set out in the previous report.

- It is expected that changes enacted by CP365 should apply to agreements already awarded as well as new agreements.

- Mitigating factors that have been considered within CP365 include ensuring a progress report is still submitted and signed by two Directors and submission of a remedial report where a SCM is moved beyond the delivery year.

Legal Text for CP365

Amendment to Chapter 12 (Monitoring)

1.1	In Rule 12.2.1

1.1.1	in paragraph (c), for “Rules 12.2.1(a) or 12.2.1(b)”, substitute “Rule 12.2.1(b)”;

1.1.2	in paragraph (ca), omit Rule 12.2.1(ca) (i)

## Prioritisation

CMAG Members determined CP365 as high priority, with an average priority score of 10.89. Members noted CP365 is a simple change to implement with low costs but high positive impacts on the CM and Participants. ITE reports can have a high frequency and likelihood for CM Participants and CP365 furthers the CM Rules Change Objectives.

## CMAG Development/Discussions

CMAG discussed CP365 at Meeting 2 and Meeting 3, below is a summary of all discussion.

CP365 will allow for a more efficient operation and administration of CM plants. For smaller CMUs, the costs associated with ITE reports can prove to be a barrier to entering the CM, and high cost of ITE reports is not justified by the delivery assurance that they provide.

There is a consequential positive impact on consumers whereby cost efficiency and savings from CP365 could be passed on to end consumers. CP365 is also determined to not have any enduring costs on CM Participants, it may reduce costs for some Participants.

- CP365 would have a positive impact on CM Participants as it encourages competition in the CM and reduces initial costs for smaller Participants entering the CM. It was noted the cost of ITE reports are the same for all Participants regardless of plant size, CP365 will therefore allow smaller plants to compete more effectively within the CM.

- A Member noted the assurance provided from ITE reports is not always of consequence compared to other mechanisms within the CM, CP365 will have a positive impact on participants by creating a more efficient scheme.

- A Member highlighted CP365 would not make the scheme less robust as CMU applications currently require up to 95% self-certification which is deemed sufficient to enter the scheme

- A Member noted CM Participants were not required to submit ITE reports during the COVID pandemic as this had been suspended and there were no issues raised as a result of this.

## Impacts & Costs

- CP365 Impacts and Benefits

| - Impact Summary |  |  |  |
| --- | --- | --- | --- |
| - Organisation | - Item | - High/Medium/Low | - Comment |
| - Delivery Body | - TBC | - TBC | - TBC |
| - LCCC/ESC | - None | - N/A | - No impact. |

- Rules

- Section 12 – Rule 12.2.1

- Costs

| - Cost Estimates |  |  |
| --- | --- | --- |
| - Organisation | - Implementation Cost (£k) | - On-Going Costs (£k/annum) |
| - Delivery Body | - TBC | - TBC |
| - LCCC/ESC | - Low | - Low |
| - Industry | - Low | - Low |
| - Total | - TBC | - TBC |

- Cross Code Impacts

- There are no known cross code impacts.

## Views against CM Rules Change Objectives and Ofgem’s Principal Objective

| - Does CP365 better facilitate the CM Rules Change Objectives and Ofgem’s Principal Objective |  |  |
| --- | --- | --- |
| - Objective | - Proposer’s View | - CMAG Views |
| - Ofgem’s Principal Objective | - Positive | - Positive |
| - Promoting investment in capacity to ensure security of electricity supply | - Positive | - Positive |
| - facilitating the efficient operation and administration of the capacity market; | - Positive | - Positive |
| - Ensuring the compatibility of capacity market rules with other subordinate legislation under Part 2 of the Act. | - Neutral | - Neutral |

## Delivery Partners Comments

LCCC/ESC have confirmed there are no expected impacts or costs to LCCC to enact CP365.

NGESO comments TBC following its Impact Assessment response.

## Implementation Date

The CMAG recommends an Implementation Date for CP365 of July 2023 or as soon as practicable afterwards if this date is not achievable.

## Recommendations

The CMAG initially recommends to the Authority:

- That CP365 should be approved;

- That CP365:

  - Better facilitates Ofgem’s Principal Objective

  - Better facilitates promoting investment in capacity to ensure security of electricity supply

  - Better facilitates the efficient operation and administration of the Capacity Market

- An Implementation Date for CP365 of July 2023 or as soon as practicable afterwards if this date is not achievable

- That the legal text for CP365 be approved.

## Appendix 1 – Key Questions for CP365

| - Questions Considered by the CMAG |  |
| --- | --- |
| - Question | - Conclusion |
| - Does the CP further the CM Rules Change Objectives? | - Members unanimously agreed CP365 furthered Ofgem’s Principal Objective. - Members unanimously agreed CP365 is positive in promoting investment in capacity to ensure security of electricity supply. - Members unanimously agreed CP365 is positive in facilitating the efficient operation and administration of the Capacity Market. - Members unanimously agreed CP365 is neutral in ensuring the compatibility of the Capacity Market Rules with other subordinate legislation under Part 2 of the Energy Act 2013. |
| - Does the CP impact on the Regulations? | - CMAG determined no impacts on the Regulations. |
| - Are there any impacts on any other central industry frameworks or obligations? | - CMAG determined no impacts on other central industry frameworks or obligations. |
| - Are there any impacts on consumers, and if so, what are the impacts? | - There is a consequential positive impact on consumers whereby cost efficiency and savings could be passed on to end consumers |
| - Does CMAG agree with the proposed solution? - Are there any suitable alternative solutions to address the defect? | - TBC |
| - What are the expected impacts on: - CM Participants? - Delivery Partners? | - CP365 would have a positive impact on CM Participants as it encourages competition in the CM and reduces initial costs for smaller Participants entering the CM. - CP365 will have a positive impact on participants by creating a more efficient scheme and reducing the administrative burden of ITE reports. |
| - What are the expected implementation/enduring costs for: - CM Participants? - Delivery Partners? | - CP365 would not have any enduring costs on CM Participants, it may reduce costs for some Participants. |
| - What are the expected timescales for implementation? | - TBC |
| - Does the draft legal text deliver the intention of the solution? | - TBC |
| - Does the CMAG recommend to Ofgem that the change be made? | - CMAG recommends Ofgem approve CP365. |