## Action Log
Action ID | Date Opened | Action | Owner | Date Due | Status | Date Closed | Action Update
1022/01 | 2022-10-18 | CMAG Secretariat to update the ToR to include expectation for Delivery Partners to attend all CMAG meetings. | Secretary | 2022-11-15 | Closed | 2022-11-15 | The CMAG Terms of Reference were updated, approved and are available to view on the website.
1022/02 | 2022-10-18 | CMAG Secretariat to include ‘CMAG Representative Updates’ as a standing agenda item for future meetings. | Secretary | 2022-11-15 | Closed | 2022-11-15 | This has been included as a standing agenda item for CMAG.
1022/03 | 2022-10-18 | Members to provide contact information on their Alternate to the CMAG Secretariat. | Members | 2022-12-13 | Closed |  | All Alternates have been confirmed, those that are not currently CMAG Members are to be ratified by Ofgem.
1022/04 | 2022-10-18 | CMAG Secretariat to publish the Change Log on the CMAG website. | Secretary | 2022-11-15 | Closed | 2022-11-15 | The CMAG Change Log is available to view on the website.
1022/05 | 2022-10-18 | CMAG Secretariat to review how other codes prioritise changes and consider alternative options for the CMAG Prioritisation Tool. | Secretary | 2022-11-15 | Closed | 2022-11-15 | An update was provided at CMAG Meeting 2 and the group agreed to progress with the CMAG prioritisation tool.
1022/06 | 2022-10-18 | CMAG Members to review the backlog of Change Proposals and provide each with a priority level of High, Medium or Low using the proposed CMAG prioritisation tool, by 1 November 2022. | Members | 2022-11-15 | Closed | 2022-11-15 | CMAG Members provided their prioritisation views and an update was provided at CMAG Meeting 2.
1022/07 | 2022-10-18 | Ofgem to review the Triton Power Change Proposal displayed on the Ofgem website. | Ofgem | 2022-12-13 | Closed |  | Triton Power has confirmed it is not seeking to raise a formal Change Proposal based on its consultation response.
1122/01 | 2022-11-15 | Ofgem and National Grid Delivery Body to provide clarity on whether mid-year CM Rules changes are allowed, and any constraints that may be in place. | Representatives | 2022-12-13 | Closed |  | Ofgem is awaiting feedback from its legal team. From an EMR DB deliverability perspective, whether a mid-year CM Rules change can be implemented by the DB will depend on the scale and nature of the change.
1122/02 | 2022-11-15 | National Grid Delivery Body to confirm how it would respond to, and the impacts on the CM of, a to partial or total market suspension. | NGESO | 2022-12-13 | Closed |  | Pursuant to Rule 8.5.1, Capacity Providers are obliged to deliver the ALFCO of their capacity committed CMU in the event of a Capacity Market Notice. They have no obligation, however, in any Settlement Period during which the Capacity Committed CMU is affected by a suspension under section G (Contingencies) of the BSC.
1122/03 | 2022-11-15 | The NGESO Representative to share details with CMAG on the NGESO User Group for Portal update testing. | NGESO | 2022-12-13 | Closed |  | Please email Firas Sultan on box.NewEMR.ITteam@nationalgrid.com to register your interest in the EMR Portal User Group.
1122/04 | 2022-11-15 | CMAG Members to provide their initial views on urgent Change Proposal CP367 and whether it should be considered further by CMAG. | Members | 2022-12-13 | Closed |  | CMAG Members views are that CP367 should not be considered further by CMAG.
1122/05 | 2022-11-15 | The Ofgem Representative to provide further information on the process and timescales for laying CM Rules Changes in parliament. | Ofgem | 2022-12-13 | Closed |  | A BEIS FAQ document on laying rules before Parliament has been circulated with the Meeting 3 paper pack.
1122/06 | 2022-11-15 | CMAG Members to review the CMAG Operating Procedure and provide any comments to the Secretariat by 25 November 2022. | Members | 2022-11-25 | Closed |  | The CMAG Operating Procedure has been circulated with the Meeting 3 paper pack.
1122/07 | 2022-11-15 | The Ofgem Representative to provide an updated view on whether CP364 should be considered Urgent. | Ofgem | 2022-12-13 | Closed |  | Ofgem's view is that CP364 should not be considered urgent.
1122/08 | 2022-11-15 | CMAG Members to consider whether any additional specific questions are required for CP364 and feedback to the CMAG Secretariat for consideration at the next meeting. | Members | 2022-11-25 | Closed |  | An update was provided at CMAG Meeting 3.
1122/09 | 2022-11-15 | CMAG Members to consider whether any additional specific questions are required for CP365 & 366, and feedback to the CMAG Secretariat for consideration at the next meeting. | Members | 2022-11-25 | Closed |  | An update was provided at CMAG Meeting 3.
1222/01 | 2022-12-13 | BEIS and Ofgem to confirm the policy intention and history of Secondary Trading being limited till after T-1 auctions (and if possible, further history on deadlines around Secondary Trading). | BEIS and Ofgem |  | In progress |  | Update to be provided at the meeting.
1222/02 | 2022-12-13 | NGESO, LCCC and EDF to confirm the proposed concept and impacts of weighted PTCO noted in CP364. | NGESO, LCCC and EDF |  | In progress |  | Update to be provided at the meeting.
1222/03 | 2022-12-13 | NGESO and Elexon to confirm its view on the impacts of CP364 on CM Credit Cover and prequalification. | NGESO and Elexon |  | In progress |  | Elexon has confirmed that moving the trading window to 6 weeks before the T-1 will have no impact on the Credit Cover process. It was also confirmed in the CMAG meeting that there would be no impact on prequalification.
1222/04 | 2022-12-13 | Elexon to provide clarity on whether DSRs turning on/off should be factored into the calculation for CP364. | Elexon |  | In progress |  | Update to be provided at the meeting.
1222/05 | 2022-12-13 | Ofgem to confirm the history of any previous concern on unintended consequences of CP364, specifically speculative bidding as a result of secondary trading. | Ofgem |  | In progress |  | Update to be provided at the meeting.
1222/06 | 2022-12-13 | NGESO to complete an impact assessment for CP364. | NGESO |  | In progress |  | Update to be provided at the meeting.
1222/07 | 2022-12-13 | Elexon to deliver the draft legal text for CP364 for CMAG Members to review. | Elexon |  | Complete |  | The draft legal text for CP364 is available in the CMAG Meeting 4 slide pack.
1222/08 | 2022-12-13 | LCCC to include additional clarity on CM suspension in the updated stress event guidance to be drafted. | LCCC |  | Complete |  | LCCC have included a section on Black Starts in the latest Stress Event Guidance document (v4.0) that was published on 21st December. Available at: https://www.emrsettlement.co.uk/document/guidance/g18-capacity-market-stress-event-guide.
1222/09 | 2022-12-13 | Elexon to update the CMAG website with the information provided by Ofgem regarding its legal limits to enact CM Rules changes. | Elexon |  | Complete |  | This information is available on the change proposals page of the CMAG website.
1222/10 | 2022-12-13 | Ofgem to confirm if the restricted component parts of CM Agreements that are grandfathered also applies to secondary trades. | Ofgem |  | In progress |  | Update to be provided at the meeting.
1222/11 | 2022-12-13 | NGESO to confirm the total number of ITE reports received in the last 5 years and what they are used for. | NGESO |  | In progress |  | Update to be provided at the meeting.
1222/12 | 2022-12-13 | NGESO to complete an impact assessment for CP365. | NGESO |  | In progress |  | Update to be provided at the meeting.
1222/13 | 2022-12-13 | Elexon to deliver the draft legal text for CP365 for CMAG Members to review. | Elexon |  | Complete |  | The draft legal text for CP365 is available in the CMAG Meeting 4 slide pack.
1222/14 | 2022-12-13 | NGESO to complete an impact assessment for CP366. | NGESO |  | In progress |  | Update to be provided at the meeting.
1222/15 | 2022-12-13 | Elexon to deliver the draft legal text for CP366 for CMAG Members to review. | Elexon |  | Complete |  | The draft legal text for CP366 is available in the CMAG Meeting 4 slide pack.
1222/16 | 2022-12-13 | Members to provide their prioritisation scores for CP368 and CP369 by Friday 16 December 2022. | CMAG Members |  | Complete |  | Update to be provided at the meeting.
1222/17 | 2022-12-13 | CMAG Secretariat to circulate a survey for feedback on CMAG meetings to all CMAG Members. | CMAG Secretariat |  | Complete |  | The CMAG Feedback Survey was circulated to all Members and Representatives on Friday 6th January 2023.
1222/18 | 2022-12-13 | CMAG Members to respond to the survey and provide feedback to the CMAG Secretariat. | CMAG Members |  | In progress |  | Members and Representatives who have not yet completed the survey are requested to do so by Friday 13th January 2023.