## Forward Work Plan
[13 empty] | 2025 | [10 empty] | 2025 | 2026 |  | 2026
Title | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | Commentary | Key
CP395 - Utilising Connection Capacity headroom for Secondary Trading | [36 empty] | Issue raised at CMAG36 |  | Pre-raise Consideration
DEVELOPMENT | [38 empty] | Initial Consideration of Proposal
Housekeeping Changes | [36 empty] | To be sent to Ofgem. Administrative changes for the Spring 2025 consultation, To be implemented for Rules (Amendement) 2025. |  | Development
Duplicate MPANs | [36 empty] | Terms of Reference for subgroup discussed at CMAG40 |  | CMAG Recommendation
Secondary Trading review | [36 empty] | Suggested scope being discussed at CMAG40 |  | CMAG Report
CP373 follow on items | [36 empty] | Dropped allowing changes to TC/DC & CMRS at CMAG 36. Replace with removing DSR Alternative Delivery Periods from P3. CMAG 26 slides 53. Also added - Standardise the use of Approved Metering Solution (AMS) and Metering Configuration Solution (MCS). |  | With Ofgem
CP399 - Capacity Provider obligations when disconnected due to Network Operator infrastructure | [36 empty] | While mitigations exist for delayed connection dates pre-delivery, there is no equivalent mitigation where connection is restricted during a Delivery Year. |  | On Hold
Removal of System Operator File 6 for Interconnector CMUs | [38 empty] | Review or Subgroup
Foreign Currancy methodology for Capex | [36 empty] | Separated out from ITE subgroup. Discussed at CMAG28 and agreed to comeback to if CMAG had future capacity. The proposal considers how transactions in non-sterling currencies should be treated for the purposes of calculating TPS or Capital Expenditure.
EPT / SPD Review | [36 empty] | Issues to be considered for grouping into Change Proposals (also maybe CP370 which is on hold): Amend Rules where granularity should be by Generating Unit or DSR Component rather than by CMU, even if the outcome is then aggregated by CMU [impacts ITE, Connection Capacity, SPD/EPT, etc.]; Ensure 3.5 Connection Capacity (CC) covers pertinent scenarios, including multiple CMUs on a site and CMUs comprising GU/Components from multiple sites, as well as DC CMUs where the basis of CC may vary between GUs; Replace 3.5.1A with an effective Site level control over CMU Connection Capacities. Clarify GCA/DCA and Connection Capacities around Refurbishing CMUs; Make 13.4A demonstrating extended performance (EPT) work more effectively; Merged with DB issues at CMAG37 - Extended Performance Unintended Consequence (trade before first test) and EPT and SPDs - New Build approach.
Wider consideration of use the use of Agents - (CP376 follow up) | [36 empty] | Looking at wider CM roles such as NEDs/consultants/advisers and whether there are any cases where sensitive information relating to bidding behaviour could potentially be shared inappropriately between parties. At CMAG#15 Ofgem noted they are considering a broader issue of how much information is shared between parties and how transparent this is, looking at data flows and bidding behaviours prior to Auction, which could feed in to future reviews with DESNZ
Extended Years Criteria Review | [36 empty] | Separated out from ITE subgroup. CMAG discussed this at CMAG29 - DESNZ and Ofgem have been provided with the Briefing document for potential future clarification of the Rules, should they choose to revisit the matter. ​ 1) Inconsistent granularity (CMU, Generating Unit, Core Generating Plant) between different Rules 2) EYC doesn’t provide for a CMU’s Capacity Agreement becoming effective after the LSD, during a Notice of Intention to Terminate period (20WD or 120WD);​ 3) Inconsistencies between Fossil Fuels & Fossil Fuel Component compared to Large Combustion Plants & BREF and other ‘combustion installations’;​ 4) Lack of clarity over Apparatus, Core Generating Plant and combustion installation;​ 5) Not being specific that BREF relates to Large Combustion Plant that may relate to one or more GU and not necessarily the whole CMU; and​ 6) Lack of clarity over the need for used plant to be on a site with a new GCA/DCA.
CP373 review Priority 5 | [36 empty] | Restructure CMMR. Standardise data retention. CMAG 26 Slides 36, 52
Prequalification Updates | [36 empty] | General area of consideration flagged by CMAG in it's initial view of issues
ON HOLD
CP356 - Facilitate Secondary Trading before CMU Termination | [36 empty] | To be considered as part of CMAG's wider review of secondary trading. The Proposer has agreed to keep this change on hold, pending the outcome of CM Rules Change Proposal CP364. @CMAG28 Ofgem said CPs will remain on hold until secondary trading position agreed with DESNZ. Most likely in 2026.
CP363 - Changes to EMR Delivery Body Portal | [36 empty] | The Proposer has agreed to keep this change on hold (email received 6/8/24). EMR DB to review and advise following Portal 2.0 roll out. Review Aug / Sept 2025 with EMR DB. Raised at Premag Aug 2024, could well be fixed now.
CP370 - Changes to Extended Performance Test | [36 empty] | At CMAG Meeting 7, DESNZ and Ofgem highlighted the policy interactions with CP367. It was agreed this Proposal would be discussed offline and not be progressed further by CMAG due to the interactions with policy. PF update - Amy email 13/6/24, which said, will remain on hold until DESNZ publish their response to their Phase 2 CM 2023 Consultation.This is because DESNZ considered changes to Extended Performance Test as part of its consultation. To ensure CMAG works and develops changes effectively, it was agreed to place this CP on hold until it was clear what DESNZ’ policy position and possible changes to EPT are. Review when EPT/SPD change comes up or 2026
CP379 - Confidential Information Definition | [36 empty] | CMAG agreed at Meeting 23, no action was required of CMAG Secretariat and the sharing of confidential information on Exhibit C would be picked up in the general Exhibit review. Await end of Exhibit Review to decide. CMAG is the proposer, Doc on CMAG SharePoint.
CPXXX - DSR Component Reallocation | [36 empty] | On hold pending outputs of DESNZ Phase 2 consultation work. DESNZ are extremely busy, review early/mid 2026. CMAG 12 - DESNZ noted they are reviewing storage as part of their phase 2 review alongside Review of Electricity Market Arrangements (REMA) developments
CPXXX - Rule 2.3.3 De-rating Factors | [36 empty] | Ofgem/DESNZ/EMR-DB in discussions to clarify policy intent. 2.3.3 relates to CP373. DESNZ are extremely busy, review early/mid 2026
CPXXX - Extension of Secondary Trading Principles for Extended Performance Testing | [36 empty] | Placed on hold as this is expected to be considered by DESNZ separately. As per CP356 (secondary trading as well) most likely to move forward, if at all, 2026
CPXXX - Managing SPDs and Secondary Trading | [36 empty] | Number of changes expected in July, as per DESNZs decision on Phase 2 consultation. Any legal drafting cannot begin until then. As per CP356 @CMAG28 Ofgem said CPs will remain on hold until secondary trading position agreed with DESNZ. Most likely in 2026.
CPXXX - Clarify the scope of 8.5.1 for Interconnectors | [36 empty] | DESNZ to clarify policy position. Review 8.5.1 to take into consideration possible System Operator restriction on Interconnector Net Output. DESNZ are extremely busy, review early/mid 2026

## Change Log
Last Updated | 27.05.2026
Change Ref | Title | Proposer | Issue | Solution | Legal Text Considered by CMAG? | Impact on Delivery Partners | Impact on Policy | Subsidy Control | Commentary | Current Stage | Ofgem Decision | Date Raised | CMAG Consultations | Statutory Consultation | CMAG Meeting discussed at | CMAG Report to Ofgem Date
CP356 | Facilitate Secondary Trading before CMU Termination | Enel-X | Existing CMUs with unforeseen delivery challenges face potential termination and associated fees before Secondary Trading is allowed to occur. Such CMUs should have the opportunity to make arrangements with an alternate provider on the secondary market so that their capacity obligation is not left unfulfilled to the detriment of consumers. | Change metering deadlines for T-4 agreements to be in line with T-1 agreements and opening up Secondary Trading for Existing and Proven DSR CMUs to prior to the relevant T-1 auction. | Yes | TBC | TBC | TBC | The Proposer has agreed to keep this change on hold, pending the outcome of CM Rules Change Proposal CP364. | On Hold | TBC | 2019-02-11 | TBC | TBC | 8
CP357 | N/A - Withdrawn | Triton Power | N/A | N/A | N/A | Not Determined | N/A | Not Determined | Confirmed with Proposer that this proposal should be withdrawn as it was a response to a Consultation. | Withdrawn | N/A | N/A | N/A | N/A | N/A
CP360 | Promoting Net Zero Assets | CCET | The least efficient assets with the smallest capital cost are being supported by the Capacity Market at the expense of new technologies and much more efficient assets. This has resulted in Gas (recipengines) peaking plant that are only 36-38% efficient being built and given 15-year contracts at the expense of batteries, tidal, pumped storage and the much more efficient CCGTs. This is at odds with our net zero goals. | The proposal is to multiply the Final capacity price by the assets' efficiency allowing those assets that can help us meet our net zero target compete against more carbon intensive assets. For example, a battery would receive the Capacity Market Price it would normally receive multiplied by ~80%, renewables would be multiplied by 100%, CCGT by ~60% and Gas peaking plant by ~36%. | Yes | Not Determined | Yes | Not Determined | At CMAG Meeting 5, Ofgem presented their view that CP360 should not be progressed on the basis that DESNZ would be better placed than the CMAG to progress a change of this magnitude. CMAG Members agreed with this rationale. | Rejected | N/A | 2021-01-29 | N/A | N/A | 5
CP362 | CM Agreement Transfers | Waters Wye Associates | Where a developer has a delivery issue, it can change the location of the site, but cannot trade the agreement to a CM party who can deliver it. As the Delivery Body do not then see the non-delivery until after a termination notice is issued, this information cannot be taken into account in wider decision making, such as setting the target capacity for future auctions. It therefore makes the delivery of CM Agreements often inefficient. | The Proposer's solution is to delete Rule 9.2.5(a)(i). The CMAG has developed an alternative solution that seeks to amend Rule 6.7.1 and Rule 9.2.5(a)(i). | Yes | EMR DB - Low CMSB - No Impact | No | No | At CMAG Meeting 5, the DESNZ representative noted the Proposer's solution for CP362 could not be implemented as secondary trading could not start until a Capacity Agreement is in place for the prospective transferor. The CMAG developed an alternative solution that it is recommended to Ofgem for implementation. | Rejected | 2025-08-21 | 2021-03-29 | N/A | TBC | 4, 5, 6, 7, 8, 9 & 11 | 2023-10-11
CP363 | Changes to EMR Delivery Body Portal | Waters Wye Associates | Currently a CM Party that owns a number of CMUs under different SPVs needs to use separate logins to manage their CMUs as each main company in the portal requires a separate login. The proposal is to allow parties to effectively manage their CMUs with one login. | Option A: EMR portal individual logins to allow access to all companies and CMUs to which the individual has been granted ‘user rights’. When the user logs in to the portal all companies (main and sub) that the login has been granted will be visible and will be manageable from the single login. Option B: CM company Directors will be able to nominate another Main company already registered on the EMR Delivery Body Portal to be a ‘CM management company’. | No | TBC | No | No | The Proposer has agreed to keep this change on hold, pending delivery of the new EMR Portal v2.0. | On Hold | TBC | 2021-04-21 | TBC | TBC | 5,6 & 8
CP364 | Allow Secondary Trading from T-4 | EDF Energy | To allow secondary trading for a Delivery Year from the conclusion of the relevant T-4 auction, rather than the conclusion of the relevant T-1 auction. Under the current Rules, the terms for secondary trades can be agreed between Parties in advance, but cannot be executed or officially recognised by the Delivery Body until the conclusion of the T-1 auction for the relevant Delivery Year. This means that the target capacity set for the T-1 auction does not take account of any potential secondary trades which could occur ahead of the Delivery Year. | Amend references within the Rules to the timing of secondary trades and transfers of Capacity Agreements. This would primarily affect Rule 3.13.1 and Rule 9.2.5(a). To account for secondary traded obligations in the capacity auctions, Rule 3.3.3, 5.5.11, and the definition of ‘Bidding Capacity’ in Rule 1.2.1 would also need to be amended. | Yes | TBC | TBC | TBC | CP364 Subgroup set up to look at technical details of solution to report back to CMAG for review and reccomendation. Due to a risk of creating an inconsistency between the Capacity Market Rules and the Regulations the CMAG chose to develop an alternative solution that allows secondary trading from T-4 on the condition that any Capacity Provider accepting a PTCO-in after the relevant T-4 but before the relevant T-1 could not enter the T-1 auction. This alternative solution is currently with EMR DB for impact assessment and is expected to be presented at the March 2024 CMAG meeting. Ofgem will speak to proposer about plans going forward and rationale for excluding this CP from 2026 Stat Con | With Ofgem | TBC | 2021-07-30 | N/A | TBC | 2, 3, 4, 14 & 18 | 2024-04-08
CP365 | Remove requirement for Independent Technical Expert report if Construction Milestones move | Engie | Rules 12.2.1 requires a Capacity Provider to submit progress reports to the EMR Delivery Body every 6 months setting out when construction milestones are expected to be achieved. If the earliest and latest dates for these construction milestones have moved by more than 2 months (a “material” change) since the last report was submitted, then an assessment is required by an Independent Technical Expert. This makes it very difficult to avoid the requirement for an Independent Technical Expert report for each progress report. | Remove the requirement for an assessment from an Independent Technical Expert if construction milestones have moved by more than 2 months from that set out in the Construction Plan in the pre-qualification application. | Yes | None | Yes - this change was included within the DESNZ CM 2023 Consultation. | No | CMAG unanimously recommended to Ofgem that CP365 be approved. In DESNZ's response to its 2023 CM Consultation, DESNZ has confirmed it intends to take forward its proposed changes to ITE Reports with an expected implementation before the 2024 CM Auctions. | Rejected | Rejected | 2022-10-13 | N/A | TBC | 2,3 & 4 | 2023-02-13
CP366 | Definition of Total Project Spend in the CM rules 2022 | Engie | New Build and Unproven DSR CMUs can include capital expenditure from 77 months before the start of the Delivery Year in their Total Project Spend. For Refurbishing CMUs, expenditure is measured from Auction Results Day to the start of the first Delivery Year. This prevents Refurbishing CMUs from including expenditure associated with the refurbishment prior to the Auction Results Day. It may mean that they cannot meet Minimum £/kW thresholds and so miss out on multi year Agreements. | Change the definition of Total Project Spend so that capital expenditure for Refurbishing CMUs can be included 77 months prior to the commencement of the first Delivery Year to which the application relates . | Yes | None | Yes - this change was included within the DESNZ CM 2023 Consultation. | TBC by DESNZ. | CMAG recommended CP366 be approved to Ofgem. In DESNZ's response to its 2023 CM Consultation, DESNZ has confirmed it intends to carry out further analysis/development on its proposed changes to the Total Project Spend definition. | Rejected | Rejected | 2022-10-13 | N/A | TBC | 2, 3 & 4 | 2023-02-23
CP367 | Fossil Fuel Emmissions Declaration | Waters Wye Associates | Existing fossil fuel generating CMUs with commercial production start dates before 4 July 2019 that exceed the Fossil Fuels Emissions Limit are unable to participate in the Capacity Market if they do not comply with the Fossil Fuel Yearly Emissions Limit (FFYEL). If generators relying on the FFYEL for participation in their CM were to maximise their output during the coming winter, it is highly likely they would exceed the FFYEL. In a very tight market, with extraordinary risks to system security, it is not in the interest of customers to discourage these generators from making themselves available when their running additional hours would still keep them with in the terms of their environmental permits. | Urgent change proposal to temporarily allow deferral of the requirement for an existing generating CMU to provide a Fossil Fuel Emissions Declaration at Prequalification until 1 month prior to the start of the Relevant Delivery Year. | Yes | Not Determined | Yes - Ofgem concluded this change is fundamentally a government policy question and therefore out of scope of CMAG work. | Not Determined | Ofgem shared its minded-to position to reject CP367 at CMAG Meeting 3. CMAG Members agreed with this position. | Rejected | Rejected | 2022-10-26 | N/A | N/A | 3
CP368 | CVR Publication and CMVRN Submission Deadline | LCCC/ESC | Currently Rule 10.5.1 requires the CM Settlement Body to publish the Capacity Volume Register at 5pm on the 10th Working day after the end of a month where an CM Stress Event occurred. This also needs to be re-published every day WD11-WD19. The issue is a small and technical one in that the intent of the rule is to allow CMVRN submissions to continue up to 5pm, however to generate and publish the CVR at 5pm ESC need 30 minutes to process the submissions, run calculations, carry out final sign offs and publish. Thus it could be argued that last submissions incorporated in the register are as of 4:30pm if this rule was followed (in practice we may be inclined not to follow this rule to allow compliance with Rule 10.2.4). Rule 10.2.4 makes it clear that all submissions up to 5pm are valid for that day. | Amend Rules 10.5.1 and 10.5.2 to allow for CVR Publication and CMVRN Submissions until 5:30pm. | Yes | Low impacts to LCCC/ESC No impact to EMR DB | No | No | CMAG recommended to Ofgem that CP368 be approved. | Implemented | yes | 2022-11-23 | N/A | 21 November 2023 – 5 January 2024 | 4 & 5 | 2023-03-15
CP369 | Secondary Trading with CMU Metering Aggregation Rules | LCCC/ESC | If CMUs secondary trade without setting up aggregation rules, and there were to be a stress event prior to CMUs setting up metering aggregation, ESC would automatically produce the maximum penalty amounts as part of the Penalties process due to there being no associated data for the CMU. Once this has occurred the Rules intentionally do not allow any retrospective adjustments to Penalties. | The proposed legal text to CP369 will: - Insert a requirement that if a secondary trade is submitted to the EMR Delivery Body (EMR-DB) after a T-1 Auction but before the start of a Delivery Year, meter aggregation rules must be set up for the transferee CMU five Working Days before the start of a Delivery Year. In the legal text this is achieved via the definition of an Approved Metering Solution, including CM Aggregation Rules. - Insert a requirement that if a secondary trade is submitted to EMR-DB within a Delivery Year, meter aggregation must be set up for the transferee CMU before submitting the transfer to the EMR-DB for registration. | Yes | Low impacts on EMR DB and LCCC/ESC. | No | No | CMAG recommended to Ofgem that CP369 be approved. | Implemented | yes | 2022-12-02 | N/A | 21 November 2023 – 5 January 2024 | 3, 4, 8 & 9 | 2023-10-02
CP370 | Changes to Extended Performance Test | Shell | Capacity Market Units (CMUs) taking multi-year Agreements containing storage must select their battery storage duration at Prequalification. CMUs can select between half an hour and 9.5 hours +, for which they are awarded different de-rating factors which determine their AACO (Auction Acquired Capacity Obligation). In order to validate battery storage durations, multi-year storage CMUs must pass an Extended Performance Test (EPT) in the first year and then every 3 years thereafter. The current methodology requires these CMUs to perform at much higher levels than their AACO and allows for minimal battery degradation. This is results in ‘early vintage’ battery storage CMUs struggling to pass their EPT and are subsequently being terminated. | This Change Proposal seeks to amend the methodology for Extended Performance Test, to better reflect the ability of storage assets to meet its contracted volume and duration. | Yes | Not Determined | Yes | Not Determined | At CMAG Meeting 7, DESNZ and Ofgem highlighted the policy interactions with CP367. It was agreed this Proposal would be discussed offline and not be progressed further by CMAG due to the interactions with Policy. | On Hold | TBC | 2023-03-13 | N/A | TBC | 7
CP371 | Protection from Very Late Network Connections | Waters Wye Associates | Rule 6.7.7 allows a Capacity Provider to extend the Long Stop Date extended day for day for any delay in achieving the Substantial Completion Milestone that results solely from a failure of a Transmission Licensee or the relevant Distribution Network Operator to provide an active connection point. Where the TO/DNO delays the connection date by over 1 year, Capacity Providers lose both revenue and effective delivery years from their CM Agreement unfairly. | The alternative solution developed by the CMAG seeks to for the case where a TL/DNO delays the connection: - Clarify that Rule 6.7.7 allows multiyear extensions to the Long Stop Date (LSD) - Allow Capacity Providers with a Prospective CMU the ability to postpone the Financial Commitment Milestone (FCM); and - Extend the period during which Capacity can be increased under Rule 6.7.6. | Yes | EMR DB - Low CMSB - Low | Proposer's legal text - Yes The CMAG Secretariat has drafted alternative solutions that do not impact on Policy. | No | The CMAG recommended to Ofgem that the CP371 alternative solution should be approved | Implemented | yes | 2023-06-07 | N/A | TBC | 9, 10, 11, 12, 13 & 14 | 2024-01-12
CP372 | Change to Rule 4.4.4 | CMAG | Rule 4.4.4 was identified as a high priority area for change by CMAG Members. CMAG Members highlighted that Rule 4.4.4 is unclear as to what is considered ‘configuration’ and therefore it is not understood what changes a CP can make to the Generating Units that comprise their CMU to ensure delivery. Rule 4.4.4 was further identified as a possible barrier to net zero, as older plants cannot change Generating Units within their CMU to adopt new, low carbon technologies on site. This is viewed as a larger issue for storage CMUs, which may need to change their configuration over time to account for battery degradation. A CMAG Member also noted Rule 4.4.4 has a particularly severe impact when aggregating small generating units; in the event that a single generating unit becomes unavailable, the whole CMU may be terminated as a result. | To amend Rule 4.4.4 to allow a CMU to change its configuration after prequalification, so long as it does not lower its derated capacity, and continues to meet its Auction Acquired Capacity Obligation (AACO). | Yes | Not Determined | No | No | This change proposal will be considered as part of a broader piece of work on Secondary Trading and Rule 4.4.4 by Ofgem and DESNZ. The CMAG agreed not to progress further with this on the basis that DESNZ expect to lead on this work as part of its Phase 2 consultation. CMAG discussions including the outcome of the industry survey will be presented to Ofgem and DESNZ | Rejected | 2025-08-21 | 2023-07-18 | N/A | TBC | 9, 10, 11 & 12 | 2024-01-24
CP373 | Process Transfer from EMR Delivery Body to CM Settlement Body | EMR Delivery Body and CM Settlement Body | In progressing the New Portal project, the EMR Delivery Body (EMR DB) has been working closely with the CM Settlement Body (CMSB) to define and deliver integrated processes. The EMR DB and CMSB have identified an opportunity to make the existing Metering processes less complex to benefit end users, reducing cost and risk, where the data owner is not the data controller. | In a joint review, the EMR DB and CMSB are recommending a transfer of roles and responsibilities from the EMR DB to the CMSB for Metering Aggregation, Metering Assessment, Metering Test and DSR Component reallocation. | Yes | EMR DB - Low CMSB - High | No | No | The CMAG recommended to Ofgem that CP373 be approved. | Implemented | yes | 2023-08-08 | N/A | 21 November 2023 – 5 January 2024 | 10, 11 & 12 | 2023-10-10
CP374 | Splitting Capacity Market Units | Waters Wye Associates | The CM Rules prohibit a change in Capacity Market Unit (CMU) configuration after Prequalification. This prevents Agreement holders from changing CMUs to reflect changes in project development and/or commercial structures. This can limit the commercial flexibility of Agreement holders, increasing the risk of project non-delivery, preventing more efficient commercial structures, and ultimately increasing Capacity Market costs. | Amend the CM Rules to allow CMUs to be split after Prequalification subject to the total Connection Capacity and Generating Technology Class (and therefore De-rated Capacity) being unchanged. Any Agreements awarded to the CMU would also be split pro-rata to the split of total Connection Capacity between the new CMUs. | No | Not Determined | Yes | Not Determined | CMAG agreed not to progress the proposal at Meeting 15 as there was a significant risk this proposal was contrary to the Regulations and policy intent (as expressed by DESNZ at CMAG Meeting 14), seen as a low priority (due to likely impact of the issues applying to a low number of sites) and work could be superseded by the wider review of Rule 4.4.4 | Rejected | 2025-08-21 | 2023-11-08 | N/A | TBC | 12, 14 & 15 | 2024-02-19
CP375 | Merging Capacity Market Units | Waters Wye Associates | CM Rules prohibit a change in Capacity Market Unit (CMU) configuration after Prequalification. This prevents Agreement holders from changing CMUs to reflect changes in project development and/or commercial structures. This may limit the commercial flexibility of Agreement holders, increasing the risk of project non-delivery, preventing more efficient commercial structures, and ultimately increasing Capacity Market costs | Amendment to the CM Rules to allow CMUs to be merged after Prequalification subject to the total Connection Capacity and Generating Technology Class of each component (and therefore De-rated Capacity) being unchanged. | No | Not Determined | Yes | Not Determined | CMAG agreed not to progress the proposal at Meeting 15 as there was a significant risk this proposal was contrary to the Regulations and policy intent (as expressed by DESNZ at CMAG Meeting 14), seen as a low priority (due to likely impact of the issues applying to a low number of sites) and work could be superseded by the wider review of Rule 4.4.4 | Rejected | 2025-08-21 | 2023-11-08 | N/A | TBC | 12, 14 & 15 | 2024-02-19
CP376 | Clarifying restrictions on the role of Agent | Ofgem | The policy intent for Rule 3.3.5 is that each single CMU or multiple CMUs who all belong to the same Group (a holding company and its subsidiaries) is represented either by the Applicant themselves or by a nominated Agent who acts as Applicant, Bidder and/or Capacity Provider for only that CMU or the CMUs of that Group. This rule is in place to ensure that those with the ability to bid in the CM auctions are acting independently so that the market remains competitive. It is currently possible and within the rules for one Group to act as an Agent for multiple CMUs from different Groups by forming subsidiaries, such as a special purpose vehicle (SPV). However, this clearly contradicts the policy intent behind Rule 3.3.5. | Amending Rule 3.3.5 to clarify that an Agent cannot also be a member of a Group (the direct or indirect Holding Company and any Subsidiary of that Holding Company) that includes a member acting as an Agent representing other Applicants. | Yes | TBC | No | No | The CMAG Secretariat is finalising legal text and Delivery Partners are conducting impact assessments. This will be considered at CMAG meeting 17 | Implemented | yes | 2023-11-22 | N/A | TBC | 15, 16, 17 & 18 | 2024-04-09
CP377 | Increasing flexibility for SPD Portfolios | EMR DB | CP377 has been raised to amend Rule 13.4.1B to allow CMU Portfolios to be formed across Company Groups. This is to allow for greater flexibility to meet the Satisfactory Performance Day (SPD) milestone. | Amending Rule 13.4.1B to allow CMU Portfolios to be formed across Company Groups. | Yes | Not Determined | No | Not Determined | EMR DB is keen to progress this CP as soon as reasonably possible as it is an existing issue. They are proposing using the existing Group definition in the rules to allow Capacity Provider Groups to use CMUs within a company group (be that relationship a direct Holding/Subsidiary or Subsidiary/Subsidiary relationship) to meet the aggregated Capacity Obligation. CMAG recommended that CP377 be implemented, pending review of final CP report. | Implemented | yes | 2024-04-09 | N/A | TBC | 19, 20 | 2024-05-08
CP378 | 50MW Limit on SPD Portfolios | CMAG | Split out from CP377. Rule 13.4.1B prevents Distribution and Transmission CMUs with aggregate connection capacity of all generating units greater than 50MW from being part of a CMU Portfolio. | Amend Rule 13.4.1B to remove 50 MW limit. Possible second part of the solution is to introduce a limit on each CMU within a CMU Portfolio. Each CMU within a CMU Portfolio must demonstrate exceeding 50 per cent of its Capacity Obligation for the requisite number of Satisfactory Performance Days in a relevant Delivery Year | Yes | Not Determined | No | No | The 50MW limit was initially introduced by the Capacity Market Expert Group to limit the aggregation of Generating Units on different sites into a single Capacity Market Unit. Removing the 50MW limit on aggregate capacity is suggested to increase flexibility for Capacity Providers to meet their Satisfactory Performance Day obligations. | Rejected | yes | 2024-07-08 | na | na | 21, 22, 23 | 2024-10-02
CP379 | Confidential Information Definition | CMAG | CM Rules Exhibit C ‘Form of Certificate of Conduct’ includes a confidentiality restriction and list of parties that CM Participants can reveal CM Confidential Information to. The list includes the EMR Delivery Body, but not the CM Settlement Body or Department for Energy Security and Net Zero. However, the CM Rules may require CM Participants to share information with both CMSB and DESNZ. | CMAG agreed no action was required of CMAG Secretariat and the sharing of confidential information on Exhibit C would be picked up in the general Exhibit review. | na | Not Determined | na | na | At CMAG 23, CMAG agreed no action was required of CMAG Secretariat and the sharing of confidential information on Exhibit C would be picked up in the general Exhibit review. | On Hold | na | 2024-07-08 | na | na | 22, 23
CP380 | Financial Commitment Milestone Extension | Penso Power | Seeks to allow a Capacity Provider to extend the deadline by when a Prospective CMU with a T-4 Agreement must demonstrate having incurred and paid 10% of Total Project Spend. | CMAG agreed to extend 10% of TPS if applied for at the appropriate time | Yes | Not Determined | na | Not Determined | Latest from Ofgem - CMAG 27 Dec 24. There are ongoing discussions around FCM in multiple areas. A detailed review of CP380 is needed to ensure a coordinated approach. Could be in a consultation following the implementation of Rules 2025 prequalification. Depend on progress of FCM. | With Ofgem | TBC | 2024-05-21 | na | na | 21, 23 | 2024-10-11
CP381 | Definition of SCEC when determining Connection Capacity | Engie | The current rule artificially constrains options for Applicants without any clear reason and is restrictive for CMUs where the sum of unit CECs exceeds station CEC. Rule 3.5.1A, which was introduced in 2023. will ensure that whichever option is used, CM connection capacity cannot exceed TEC or MEC. | Under this proposal, SCEC can be determined from either the sum of each Generating Unit’s CEC as it is now or station CEC. This will allow CMUs which have unit CECs that collectively sum to more than station CEC another option to reflect the connection capacity of their CMUs. | Yes | Not Determined | na | No | To ensure equitable treatment for Distribution CMUs, a similar change is proposed for Distribution CMUs (SCEC can be the registered capacity of the power station side or sum of registered capacities of individual units that comprise that power station). The proposer is happy to not include this second part if this presents problems for Distribution CMUs. | Implemented | yes | 2024-04-10 | na | na | 22, 23 | 2024-10-16
CP382 | ITE Reporting Requirements | EMR DB | This CP looks to address: Significant variance in the nature of ITE providers; Significant variance in the nature of ITE reports submitted to EMR DB; EMR DB has limited powers to reject poor quality ITE reports; Suitability of ITE reporting requirements; Level of Assurance. | Update the ITE definition to remove the requirement for international experience; Move to a report template based approach. The proposer contends that this is easier for both the ITE to complete and for the Delivery Body to assess whilst still confirming a similar level of checks from one ITE to another | Yes | TBC | na | No | ITEs and Capacity Providers that are required/wish to use CM Rules provisions which require ITEs | With Ofgem | TBC | 2024-09-09 | na | na | 20 - 24, 29 | 2025-09-04
CP383 | Change to the CM Register to add storage durations | Waters Wye Associates | Storage technologies are unique from other Generating Technology Classes (GTCs) as they can declare their connection capacity and their selected GTC’s duration has a major impact on their de-rating factor and Extended Performance Testing. However, it is unclear whether self-declarations are being understated or overstated as Capacity Market Registers (CMRs) lack these details. This lack of transparency during pre-qualification and post-auction(s) is causing an issue whereby it is hard to track the importance of storage technologies as there is missing information in CMRs that could help develop an understanding of their significance to the security of supply. | Amending Capacity Market (CM) Rule 7.4.1. to include the publication for all storage technologies part of the CMRs. This would create transparency on what is being declared by storage technologies for pre-qualification and post-auction(s). | na | na | na | na | Ideally the proposer would make this retrospective as it would seem useful to Government, NESO and the market to be easily able to look at ALL of the storage in the CM. To give greater clarity around the contracted CMUs, the CM Register would include the duration of the storage assets as submitted at pre-qualification and reported in the auction results. | Rejected | 2025-08-21 | 2024-10-23 | na | na | 26 | 2025-01-23
CP384 | Change to termination events 6.10.1 (g) & (ga) | Waters Wye Associates | Lack of clarity for Rule 6.10.1 (g) and (ga). Capacity Providers are having to maintain TEC of a site comprising multiple CMUs sharing a common GCA, even if one CMU’s Agreement had been terminated for whatever reason | Replaced 'any other' CMUs, with 'Capacity Commited' CMUs into both termination events | yes | na | na | na | Simple solution recommended | With Ofgem | TBC | 2024-10-11 | na | na | 25, 26, 27, 28 | 2025-03-03
CP385 | Update to Load Following Capacity Obligation calculation inputs | EMR DB | This change proposes to update the LFCO calculation reference to the term RfR (Reserve for Response) with a reference to Reserve and Response (RaR) for largest loss, which is what is currently reported by the Delivery Body in the Electricity Capacity Report (ECR). | Update the term used in the LFCO calculation to be RaR as well as its definition in the legal text. Add wording into the legal text that clarifies RaR will be associated with the Base Case published in the Electricity Capacity Report (ECR) and introduce wording into the legal text to clarify that the applicable RaR is the one published in the most recent ECR that contains that Delivery Year. | yes | na | na | na | Straightforward, passed to Ofgem | With Ofgem | TBC | 2024-12-02 | na | na | 23, 27 | 2025-01-23
CP386 - CP373 review Priority 1 | Alignment of Metering Test Processes, DSR Delivery Periods and Terminology | CMAG | Clarity on who is responsible for initiating a Metering Test, Clarity on the timeframe for DSR CMUs submitting metering information. Clarity on when CMSB notify DB of the outcome of any Metering Test, 8.3.3(da) and 13.3.10 are inconsistent. Clarity on the process for issuing a Metering Test Certificate. | The proposed changes align the rules with the updated processes introduced by CP373, remove redundancy, and ensure consistency in language and responsibilities. | na | na | na | na | Straightforward, passed to Ofgem | With Ofgem | TBC | 2025-04-01 | na | na | 31, 32 | 2025-06-03
CP 387 - CP373 review Priority 2 | Metering Assessment Deadlines | CMAG | CP373 has retained the deadline for Metering Assessments as the Long Stop Date (LSD), however under 6.8.2 a CMU can meet MCR within 120 WD of LSD. Metering Declaration in MyEMRS. | To resolve the deadline misalignment for Metering Assessment, it is proposed a new Rule is introduced that addresses the misalignment. To clarify for Capacity Providers, when they can and should obtain a Metering Assessment. | na | na | na | na | Straightforward, passed to Ofgem | With Ofgem | TBC | 2025-04-01 | na | na | 31, 32 | 2025-06-03
CP388 | Conditional Prequalification due to connection reform | DESNZ | Any New Build CMU on the Transmission Network with a Grid Connection Agreement for after 1 October 2029 could not prequalify for the upcoming T-4 Auction. Due to NESO’s Connection Reform Package, which will accelerate grid access for viable energy generation projects, New Build assets will begin to learn their position in the reformed connection queue from September 2025, likely after the Prequalification Window closes. | Government proposes allowing Transmission Network Connected New Build CMUs that do not currently have a Grid Connection Agreement that would allow them to be connected by 2029/2030, but that have requested an accelerated connection date from NESO, to submit an Application during the 2025 Prequalification Submission Window. | na | na | na | na | This is being raised as an Urgent Change Proposal, so is not utilising CMAG | Implemented | 2025-07-25 | 2025-06-19 | na | na | 34 | na
CP389 | Connection Capacity Review | Uniper | Surgery Items to discuss questions raised by CMAG Secretatriat on Rule 3.5 | The solution has multiple elements. Please see CP report for summary | Yes | na | na | na | Passed to Ofgem | With Ofgem | TBC | 2025-07-09 | na | na | 27- 34 | 2025-09-02
CP390 | Simpifying the Reporting and Monitoring provisions in the CM Rules | CMAG | A successful Applicant, as Capacity Provider with a Capacity Agreement, must provide progress reports every six months to the DB indicating how progress to Construction Milestones has or is being achieved for their Prospective CMU. Where there are material changes to the original schedule from the Application, or since the last report, a CP should accompany their report with an explanation as to why. | The proposal seeks to simplify the reporting and monitoring provisions for Capacity Providers with Prospective CMUs in the CM Rules to reduce their administrative burden and improve clarity for delivery assurance | Yes | na | na | na | Seperated out from ITE subgroup. Developed via SharePoint. | With Ofgem | TBC | 2025-02-18 | na | na | 29, 32, 35 | 2025-09-04
CP391 | Enabling the use of MHHS services for Supplier Settlement Metering Confirguration Solutions | CMAG | The Capacity Market (CM) Rules do not mention MHHS systems, processes, data flows, or agent roles. This oversight poses a problem because starting from M10, Metering Systems will begin to migrate and subsequently utilise MHHS services | The changes should include adding the new MHHS services into the CM Rules, 1.2 Definitions. Additionally, the definition of “Supplier Metering Configuration Solution”, must be amended to enable the use of new MHHS services. | Yes | no | no | no | Ofgem confirmed at CMAG 35 (19/8/25) that these issues will be treated as Urgent | With Ofgem | TBC | 2025-03-18 | na | na | 30, 31, 33, 34 | 2025-08-18
CP392 | Allow BSC Code of Practice 11 Asset Metering | LCCC/ESC | As the use of Asset Metering (domestic DSR Components) for decentralised storage and flexibility evolves throughout markets, because the Half-Hourly settlement requirement for associated Boundary Point Metering Systems is removed. This will create a significant and insurmountable operational bottleneck for testing. | Code of Practice 11 compliant meters have their metering guaranteed and assured under the BSC. Therefore, this change would enable the use of BSC-compliant metering, which is installed, commissioned and read by BSC Qualified Agents, who are all assured through the BSC Performance Assurance Framework (PAF) | Yes | yes | no | no | Ofgem confirmed at CMAG 35 that this issue will proceed as a standard CMAG Change Proposal. | With Ofgem | TBC | 2025-06-17 | na | na | 33, 34 | 2025-09-19
CP393 | Full Review of CM Exhibits | Ofgem | To ensure that the Capacity Market (CM) Exhibits are consistent with the CM Rules, use exact required language, and are made simpler and clearer for stakeholders | This Change Proposal reviews each Exhibit in detail. | Yes | no | no | no | CMAG Recommended solution at CMAG35, as long as there are no material changes in CP report review. | With Ofgem | TBC | 2024-10-15 | na | na | 26-35 | 2025-09-04
CP394 | 2026 Conditional Prequalification for assets that have applied for a new or modified connection date | EMR DB | It is possible that some projects that wish to enter the CM would apply for a new or modified connection agreement (CMP434), but not be informed of the outcome before the CM Prequalification 2026 window closes. | EMR DB proposes extending the Conditional Prequalification option that was put in place for PQ25, amending the previous Rule change to capture differences between the Connections Reform process and any future connections application window, as well as lessons learned through implementation of the Conditional PQ Rules for PQ25 | Yes | yes | no | no |  | With Ofgem | TBC | 2025-12-01 | na | na | 38, 39 | 2026-01-09
CP395 | Utilising Connection Capacity headroom for Secondary Trading | VPI | This proposal seeks to allow Capacity Market Units (CMUs) that experience an increase in their Connection Capacity after Prequalification to utilise this additional “Headroom Capacity” for secondary trading. | The proposal introduces a targeted mechanism that allows verified increases in Connection Capacity to be qualified as an Eligible Secondary Trading Entrant (STE) for the relevant Delivery Year. | yes | yes | no | no |  | With Ofgem | TBC | 2025-09-13 | na | na | 36, 37, 38, 39 | 2026-01-15
CP396 | Total Project Spend review | BW ESS | A change proposal to take on the final issues of the CMAG Secretariat Total Project Spend review. Plus the issue of how delays in network connections (6.7.7), affect the TPS Qualifying Capital Expenditure window. | This has four separate issues. The solutions for each are varied and can be found in the Change Proposal form on Change Proposal webpage. | Yes | yes | no | no |  | With Ofgem | TBC | 2025-12-09 | na | na | 29, 36, 38, 39 | 2026-01-09
CP397 | Extension to the 16-month Financial Commitment Milestone for New Build Projects with a scheduled first Delivery Year starting on 1 October 2028 or 1 October 2029 | DESNZ | Government acknowledges that some projects may face challenges in meeting their FCM if they do not have a guaranteed connection date set out in a revised connection offer, even if the connection agreement date must be before the end of 2030. | This proposal will provide New Build CMUs that won CM Agreements in the T-4 auction held in 2025 or win a CM Agreements in the T-4 auction held in 2026, an additional 12 months to complete their FCM. This will make the 16-month deadline to meet the FCM a 28-month deadline instead and would give a project due to start their agreement on 1 October 2028, until July 2027 to meet their FCM. This applies only where the CMUs original connection date has been moved following the queue reformation process. | Yes | na | na | na | This is being raised as an Urgent Change Proposal, so is not utilising CMAG. | With Ofgem | TBC | 2026-01-27 | na | na | 41 | na
CP398 | Enabling Capacity Providers to utilise their own Meter Operator Agent | LCCC/ESC | This proposal seeks to introduce an optional pathway for Capacity Providers to have their Metering Statements (Schedule 6) completed and verified by an authorised Meter Operator Agent, rather than solely by the Settlement Body and the Metering Agent that undertakes work on behalf of the Settlement Body | The proposed solution is to change the CM Rules to enable a Capacity Provider to choose to have their Metering Statement (Schedule 6) verified by an independent Meter Operator Agent rather than by the Settlement Body’s Metering Agent, whilst the current approach still remaining as an option. | no | na | na | na | This was discussed at CMAG 41 only and passed to Ofgem to be included in the March 2026 Stat Con | With Ofgem | TBC | 2026-02-05 | na | na | 41 | na
CP399 | Capacity Provider obligations when disconnected due to Network Operator infrastructure | Drax Power Limited / EDF Energy | The Rules do not include mitigation's for testing or the obligation to deliver during a System Stress Event, when a Capacity Obligated CMU connections is interrupted due to an event impacting the TL or DNO infrastructure and where the remedy is the sole responsibility of the TL or DNO. | Amend Rules 8.5.1(c) and 13.4.1 to include mitigations for meeting Satisfactory Performance Testing and obligations to deliver in System Stress Event when a Capacity Obligated CMU’s connection is interrupted due to an event impacting the Network Operators infrastructure and where the remedy is the sole responsibility of the Network Operator. |  |  |  |  | Case for Urgency discussed at CMAG42. CMAG recommended urgency and letter request for urgency sent to Ofgem 24 March. | Development | TBC | 2026-02-23 | na | na | 41, 42, 43

## Guidance
Description
Change Ref | The unique reference number assigned to each CM Rule Change Proposal
Title | The title of the CMs Rule Change Proposal
Proposer | The organisation that raised the CM Rules Change Proposal
Problem/Issue | A short (3 or 4 sentences) description of the problem/issue that the CM Rules Change Proposal seeks to address
Solution | A short (3 or 4 sentences) description of the solution that the CM Rules Change Proposal describes to address the Problem/Issue in the Change Proposal
Legal Text Considered by CMAG | This is 'yes' if legal text has been reviewed by CMAG. Please note that this does not indicate whether the CMAG believe a particular CM Rules Change Proposal should be implemented or not.
Impacts on Delivery Partners | This indicates whether a proposal is expected to impact a Delivery Partner. The Delivery Partners are: National Grid Electrcity System Operator - Delivery Body (EMR DB); and Electrcity Settlements Company/Low Carbon Contracts Company (ESC/LCCC)
Impact on Policy | This indicates whether the proposal is expected to have a direct impact on Government policy and/or the Regulations. If a proposal is deemed to impact Policy the proposal is considered out of scope for the CMAG.
Subsidy Control | This indicates whether a proposal impacts the subsidy control framework
Commentary | Contains a record of relevant actions and key updates in the progression of the CM Rules Change Proposal
Current Stage | There are 6 possible stages in the development of a CM Rule Change Proposal. These are: Submission: This is the stage after a CM Rule Change Proposal has been formally raised but before the CMAG has considered the proposal at a meeting. Scheduled: This is the stage after the CMAG has initially considered the CM Rule Change Proposal but prior to the CMAG beginning development work on the proposal or the proposal is sent to consultation. CMAG Development: This is the stage after the CMAG has initially considered the CM Rule Change Proposal and has determined that further assessment is required of the proposal. Activities in this stage may include the development of possible solution options, the development of legal text for a proposal and/or the consideration of the impacts of a solution on relevant stakeholders. Consultation: This is the stage after the CMAG has initially considered a proposal or following the conclusion of the CMAG development stage where the legal text and relevant accompanying documents (if applicable) is circulated to all stakeholders for further engagement and responses are invited to a series of relevant questions. This stage is optional and only required if the CMAG determine that there is a need to circulate prior to Ofgem's statutory consultation. With Ofgem: This is the stage after the consultation and after the CMAG has sent a recommendation to Ofgem but before Ofgem has determined whether to approve/reject/send back a CM Rules change Withdrawn: If a proposal was raised and then withdrawn by the proposer.
Ofgem Decision | Ofgem will decide whether to approve/reject/send back a CM Rules Change Proposal. If Ofgem has not yet made a decision on a CM Rules Change Proposal this is TBC
Date Raised | This is the date the CM Rules Change Proposal was raised
CMAG Consultations | This is the start and end date of any CMAG consultations that have been issued. Where no CMAG consultation is required this is N/A
CMAG Report to Ofgem Date | The date the CMAG report is sent to Ofgem
Statutory Consultation | This is the start and end date of the statutory consultation on a CM Rules Change Proposal that have been issued by Ofgem. Where no statutory consultation has taken place yet this is TBD
CMAG Meeting Discussed at | Contains a record of which CMAG meetings the CM Rules Change Proposal was discussed at. The purpose of this is so that stakeholders can easily find/access relevant meeting documentation easily
Comments | A free text field for any relevant comments

## Sheet2
| 2025 |  |  |  | 2026
Title | September | October | November | December | January
CP392 - CoP 11 Asset Metering
Housekeeping Changes
CP373 review Priority 3
Utilising Connection Capacity headroom for Secondary Trading
CP373 review Priority 4
CP373 review Priority 5
EMRS issue over AACO v PTCO-out
Total Project Spend
CP in line with DESNZ consultation (Section 4)
EPT / SPD Review
Wider consideration of use the use of Agents - (CP376 follow up)
Foreign Currancy methodology for Capex
Extended Years Criteria Review
Prequalification Updates
| 2025 |  | 2026
Title | November | December | January | February | March | April | May
Housekeeping Changes
CP394 - CP373 review Priority 3
Total Project Spend
Utilising Connection Capacity headroom for Secondary Trading
EMRS issue over AACO v PTCO-out
CP373 review Priority 4
CP373 review Priority 5
EPT / SPD Review
Wider consideration of use the use of Agents - (CP376 follow up)
Foreign Currancy methodology for Capex
Extended Years Criteria Review
Prequalification Updates